## IXIN
Objectif :
Vérification historique publication de la plaque CEMRH3CT_0069

## IXISPI_CEM
Code IMB | ID Chantier | NB_EL | Clé site | Statut Syndic | Action | Réalisation | Lancement | BPT | Etude | Probation | Qualif
IMB/73011/X/01VJ | 4495013 | 12 | DTERPA | OK | Realisation | OK | OK | OK | OK | NOK | OK
IMB/73011/X/02JX | 4495324 | 1 | DTERPA | OK | Realisation | OK | NOK | NOK | NOK | NOK | NOK
IMB/73011/X/02K4 | 4495330 | 1 | DTERPA | OK | Realisation | OK | NOK | NOK | NOK | NOK | NOK
IMB/73011/X/02JY | 4495325 | 1 | DTERPA | OK | Realisation | OK | NOK | NOK | NOK | NOK | NOK
IMB/73011/X/02KU | 4495338 | 1 | DTERPA | OK | Realisation | OK | OK | NOK | OK | NOK | NOK
IMB/73011/X/00DE | 4494318 | 4 | DTERPA | OK | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/00FQ | 4494324 | 2 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/00FR | 4494325 | 3 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/00FS | 4494326 | 14 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/00FT | 4494327 | 1 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/00FU | 4494328 | 1 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/00FV | 4494329 | 1 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/00FW | 4494330 | 1 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/00WB | 4494562 | 13 | DTERPA | OK | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/00WD | 4494563 | 11 | DTERPA | OK | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/00XI | 4494573 | 10 | DTERPA | OK | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/010F | 4494646 | 9 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/010G | 4494647 | 8 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/010H | 4494648 | 10 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/010I | 4494649 | 10 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/014F | 4494666 | 6 | DTERPA | OK | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/0178 | 4494717 | 27 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/018I | 4494721 | 33 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01BO | 4494774 | 3 | DTERPA | OK | Lancement | SO | OK | NOK | OK | NOK | NOK
IMB/73011/X/01BP | 4494775 | 3 | DTERPA | OK | Lancement | SO | OK | NOK | OK | NOK | NOK
IMB/73011/X/01BQ | 4494776 | 3 | DTERPA | OK | Lancement | SO | OK | NOK | OK | NOK | NOK
IMB/73011/X/01BR | 4494777 | 2 | DTERPA | OK | Lancement | SO | OK | NOK | OK | NOK | NOK
IMB/73011/X/01C0 | 4494784 | 17 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01NK | 4494889 | 12 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01NL | 4494890 | 14 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01NM | 4494891 | 12 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01NN | 4494892 | 12 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01NO | 4494893 | 12 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01NP | 4494894 | 12 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01TF | 4494989 | 4 | DTERPA | OK | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01W3 | 4495015 | 7 | DTERPA | OK | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01W5 | 4495016 | 3 | DTERPA | OK | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01W8 | 4495017 | 10 | DTERPA | OK | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01WF | 4495018 | 7 | DTERPA | OK | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01XE | 4495026 | 20 | DTERPA | OK | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01YB | 4495035 | 6 | DTERPA | OK | Lancement | SO | OK | OK | OK | OK | OK
IMB/73011/X/020R | 4495079 | 66 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/020S | 4495080 | 64 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/020T | 4495081 | 64 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | NOK | OK | NOK | OK
IMB/73011/X/023Y | 4495173 | 7 | DTERPA | OK | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/02DL | 4495262 | 6 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/02DM | 4495263 | 10 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/02E1 | 4495278 | 12 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/02K1 | 4495327 | 3 | DTERPA | OK | Lancement | SO | OK | NOK | OK | NOK | NOK
IMB/73011/X/02LL | 4495346 | 2 | DTERPA | OK | Lancement | SO | OK | NOK | OK | NOK | NOK
IMB/73011/X/02LM | 4495347 | 2 | DTERPA | OK | Lancement | SO | OK | NOK | OK | NOK | NOK
IMB/73011/X/00FX | 4494331 | 6 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/00FY | 4494332 | 1 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/00WU | 4494565 | 5 | DTERPA | OK | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/010J | 4494650 | 10 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01BS | 4494778 | 1 | DTERPA | OK | Lancement | SO | OK | NOK | OK | NOK | NOK
IMB/73011/X/01BV | 4494779 | 30 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/01BX | 4494781 | 15 | DTERPA | NON_EFFECTUE | Lancement | SO | OK | OK | OK | NOK | OK
IMB/73011/X/000O | 4494204 | 9 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/000P | 4494205 | 1 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/0034 | 4494221 | 12 | DTERPA | EN_COURS | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/0036 | 4494223 | 13 | DTERPA | EN_COURS | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/003G | 4494233 | 14 | DTERPA | EN_COURS | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/003H | 4494234 | 12 | DTERPA | EN_COURS | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/003T | 4494245 | 12 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/003U | 4494246 | 12 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/0068 | 4494271 | 1 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/0069 | 4494272 | 1 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/006A | 4494273 | 1 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/006B | 4494274 | 1 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/006C | 4494275 | 1 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/006D | 4494276 | 1 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/00E9 | 4494322 | 6 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/00KA | 4494342 | 4 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/00NV | 4494436 | 10 | DTERPA | EN_COURS | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/00RG | 4494491 | 14 | DTERPA | EN_COURS | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/00RH | 4494492 | 18 | DTERPA | EN_COURS | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/00VG | 4494533 | 15 | DTERPA | EN_COURS | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/00XW | 4494586 | 4 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/013B | 4494654 | 21 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/013K | 4494663 | 6 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/013L | 4494664 | 6 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/0165 | 4494683 | 11 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/0166 | 4494684 | 11 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/0167 | 4494685 | 15 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/0168 | 4494686 | 14 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/0169 | 4494687 | 15 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/016A | 4494688 | 10 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/016B | 4494689 | 12 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/016C | 4494690 | 9 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/016D | 4494691 | 8 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/016W | 4494710 | 9 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/016Y | 4494712 | 7 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/018P | 4494727 | 10 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/018Q | 4494728 | 10 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/018R | 4494729 | 9 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/018T | 4494731 | 8 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/018U | 4494732 | 8 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/018V | 4494733 | 9 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/019A | 4494743 | 10 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/019B | 4494744 | 10 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/019C | 4494745 | 10 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/019D | 4494746 | 10 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/019E | 4494747 | 10 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/01A6 | 4494758 | 5 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/01UF | 4494995 | 25 | DTERPA | EN_COURS | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/01UG | 4494996 | 25 | DTERPA | EN_COURS | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/01ZE | 4495055 | 6 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/024M | 4495175 | 4 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/02AB | 4495198 | 4 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/02AP | 4495213 | 19 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/02C0 | 4495236 | 28 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/02C1 | 4495237 | 22 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/02D8 | 4495249 | 6 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/02DQ | 4495267 | 11 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/02JL | 4495322 | 7 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/02K2 | 4495328 | 5 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/02K3 | 4495329 | 6 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/02KR | 4495335 | 21 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/006R | 4494278 | 6 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/016K | 4494697 | 11 | DTERPA | NON_EFFECTUE | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/019F | 4494748 | 10 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/02KS | 4495336 | 3 | DTERPA | OK | BPT | SO | SO | OK | OK | NOK | OK
IMB/73011/X/002T | 4494210 | 22 | DTERPA | EN_COURS | Etude | SO | SO | SO | OK | NOK | OK
IMB/73011/X/003S | 4494244 | 17 | DTERPA | NON_EFFECTUE | Etude | SO | SO | SO | OK | NOK | OK
IMB/73011/X/01B9 | 4494772 | 9 | DTERPA | OK | Etude | SO | SO | SO | OK | NOK | OK
IMB/73011/X/01NT | 4494897 | 16 | DTERPA | EN_COURS | Etude | SO | SO | SO | OK | NOK | OK
IMB/73011/X/01NV | 4494899 | 16 | DTERPA | EN_COURS | Etude | SO | SO | SO | OK | NOK | OK
IMB/73011/X/01NW | 4494901 | 16 | DTERPA | EN_COURS | Etude | SO | SO | SO | OK | NOK | OK
IMB/73011/X/024V | 4495177 | 29 | DTERPA | EN_COURS | Etude | SO | SO | SO | OK | NOK | OK
IMB/73011/X/01NR | 4494895 | 16 | DTERPA | EN_COURS | Etude | SO | SO | SO | OK | NOK | OK
IMB/73011/X/000R | 4494206 | 16 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/000S | 4494207 | 15 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/002V | 4494212 | 27 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/002X | 4494214 | 22 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/002Y | 4494215 | 19 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/002Z | 4494216 | 21 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0030 | 4494217 | 37 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0031 | 4494218 | 31 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/003V | 4494247 | 21 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/003W | 4494248 | 15 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/004O | 4494252 | 10 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/006Q | 4494277 | 4 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00AR | 4494307 | 5 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00BK | 4494316 | 5 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00BN | 4494317 | 5 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00DY | 4494320 | 2 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00GX | 4494334 | 9 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00GY | 4494335 | 8 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00H0 | 4494336 | 9 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00LC | 4494367 | 16 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00LG | 4494371 | 28 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00LJ | 4494374 | 32 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00LK | 4494375 | 29 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00LM | 4494377 | 23 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00LO | 4494379 | 24 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00NQ | 4494431 | 18 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00O1 | 4494442 | 14 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00O3 | 4494444 | 15 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00O6 | 4494447 | 15 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00O7 | 4494448 | 13 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00O8 | 4494449 | 17 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00O9 | 4494450 | 23 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00OA | 4494451 | 25 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00RC | 4494487 | 22 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00RK | 4494495 | 19 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00RL | 4494496 | 30 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00RM | 4494497 | 11 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00RN | 4494498 | 12 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00SL | 4494516 | 3 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00SO | 4494517 | 7 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00SQ | 4494518 | 5 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00SR | 4494519 | 1 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00WX | 4494567 | 7 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00YM | 4494613 | 16 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00YR | 4494618 | 14 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00YT | 4494620 | 9 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00ZF | 4494641 | 79 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/00ZJ | 4494642 | 6 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/012W | 4494651 | 5 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/012X | 4494652 | 1 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0160 | 4494682 | 4 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/016P | 4494703 | 13 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/016R | 4494705 | 12 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/016S | 4494706 | 14 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/016T | 4494707 | 13 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0172 | 4494714 | 18 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0175 | 4494715 | 17 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/018K | 4494722 | 11 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/018N | 4494725 | 13 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/01DX | 4494804 | 4 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/01HT | 4494871 | 17 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/01I3 | 4494873 | 6 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/01VF | 4495012 | 7 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/01WQ | 4495019 | 4 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/01WW | 4495020 | 5 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/01XH | 4495027 | 9 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/01XK | 4495030 | 21 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/01XM | 4495032 | 10 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/01XO | 4495034 | 25 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/020J | 4495075 | 10 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/020K | 4495076 | 9 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/020V | 4495083 | 9 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/020W | 4495084 | 11 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/020X | 4495085 | 10 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/020Y | 4495086 | 10 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0219 | 4495092 | 7 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/021V | 4495114 | 4 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0221 | 4495119 | 15 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0222 | 4495120 | 10 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0223 | 4495121 | 15 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0224 | 4495122 | 5 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/022F | 4495131 | 16 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/022M | 4495137 | 9 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/022N | 4495138 | 20 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/023O | 4495171 | 4 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/023U | 4495172 | 6 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/024W | 4495178 | 27 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/024Y | 4495180 | 9 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/024Z | 4495181 | 19 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0250 | 4495182 | 17 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0251 | 4495183 | 43 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0252 | 4495184 | 22 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0253 | 4495185 | 42 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/0254 | 4495186 | 17 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/027L | 4495193 | 4 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02AC | 4495199 | 10 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02AL | 4495209 | 13 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02AM | 4495210 | 13 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02AN | 4495211 | 13 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02AO | 4495212 | 13 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BC | 4495217 | 14 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BD | 4495218 | 13 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BE | 4495219 | 17 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BF | 4495220 | 13 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BG | 4495221 | 25 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BH | 4495222 | 16 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BI | 4495223 | 14 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BJ | 4495224 | 19 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BK | 4495225 | 14 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BL | 4495226 | 24 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BM | 4495227 | 14 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BN | 4495228 | 15 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BO | 4495229 | 22 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02BP | 4495230 | 16 | DTERPA | OK | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02C7 | 4495242 | 6 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02DG | 4495257 | 19 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02DH | 4495258 | 22 | DTERPA | EN_COURS | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02DN | 4495264 | 6 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02DS | 4495269 | 23 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02DT | 4495270 | 5 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02DV | 4495272 | 3 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02FS | 4495296 | 14 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02W1 | 4495431 | 16 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02W2 | 4495432 | 18 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02W3 | 4495433 | 16 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02W4 | 4495434 | 18 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02W5 | 4495435 | 16 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO
IMB/73011/X/02W6 | 4495436 | 16 | DTERPA | NON_EFFECTUE | Qualif | SO | SO | SO | SO | OK | SO

## Synthese
CEMRH3CT_0091
Actions publiées | Nb code IMB publiés par action | Nb code IMB publiés par action avec anomalie | Nb code IMB non publiés Qualif négo | Nb code IMB non publiés Probation | Nb code IMB non publiés Réalisation étude | Nb code IMB non publiés BPT | Nb code IMB non publiés Lancement travaux | Nb code IMB non publiés Réalisation travaux | Nb code IMB non publiés TFX
Qualif négo | 241 | 0
Probation | 1 | 0
Réalisation étude | 128 | 0
BPT | 110 | 65 | 0 | 65 | 0
Lancement travaux | 55 | 0 |  |  | 0
Réalisation travaux | 5 | 6 |  |  | 3 |  | 3
TFX | 0 | 0 |  |  | 0 |  | 0 | 0